## Gantt Chart
| Project Start Date: |  | 2026-01-05
| Project Name: |  | FYP Electrical Panel Monitoring System | [5 empty] | 2026
[7 empty] | Week Starting: |  | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  |  | Apr |  |  |  | May |  |  |  | Jun
[9 empty] | 2026-01-05 | 2026-01-12 | 2026-01-19 | 2026-01-26 | 2026-02-02 | 2026-02-09 | 2026-02-16 | 2026-02-23 | 2026-03-02 | 2026-03-09 | 2026-03-16 | 2026-03-23 | 2026-03-30 | 2026-04-06 | 2026-04-13 | 2026-04-20 | 2026-04-27 | 2026-05-04 | 2026-05-11 | 2026-05-18 | 2026-05-25 | 2026-06-01 | 2026-06-08 | 2026-06-15 | 2026-06-22 | 2026-06-23
# | Activity | Description | Assigned To | Start | End | Days | Status | Done
1 | Project Initiation | Complete PID, finalize requirements, set up dev environment | Edwin | 2026-01-05 | 2026-01-18 | 14 | Not started | 90%
2 | Research & Design | Literature review, system architecture, database schema design | Edwin | 2026-01-19 | 2026-02-15 | 28 | Not started | 0%
3 | Hardware & Firmware Dev | ESP32 prototype, sensor integration, RFID, MQTT comms | Edwin | 2026-02-16 | 2026-03-22 | 35 | Not started | 0%
4 | Backend Development | MQTT broker setup, API development, database implementation | Edwin | 2026-03-23 | 2026-04-19 | 28 | Not started | 0%
5 | Frontend Development | Web dashboard UI, panel selection, real-time data display | Edwin | 2026-04-20 | 2026-05-10 | 21 | Not started | 0%
6 | Message Alert Integration | Alert notification integration, triggering logic | Edwin | 2026-05-11 | 2026-05-18 | 8 | Not started | 0%
7 | Integration & Testing | System integration, comprehensive testing, bug fixing | Edwin | 2026-05-18 | 2026-06-01 | 15 | Not started | 0%
8 | Documentation & Report | Final report writing, user documentation | Edwin | 2026-06-01 | 2026-06-15 | 15 | Not started | 0%
9 | Submission | Final report submission - 23 June 2026 | Edwin | 2026-06-22 | 2026-06-23 | 2 | Not started | 0%